# Risk assessment plan

| School/workplace | Newcastle High School |  |  | Condition, task, activity or event | Full-day music excursion: Attendance at the Sydney Symphony Orchestra Daytime Schools Concert at the Sydney Opera House, including return travel by chartered coach from school to Circular Quay and supervised participation in a live orchestral performance and related educational activities. |
| --- | --- | --- | --- | --- | --- |
| Principal/workplace manager | NA |  |  |  |  |
| Assessed by | NA | Date | NA | Location | Sydney Opera House |
| Approved by | NA | Date | NA | Review date | NA |
| WHS Risk Register update | NA | Date | NA | Prepared in consultation with | NA |

Risk Management process

| Hazard/s | Risk/s | Risk rating | Control action/s | Risk rating after controls | Responsible | Due | Complete |
| --- | --- | --- | --- | --- | --- | --- | --- |
| What presents the potential risk to health and/or safety? | What might happen, how likely is it and what could be the consequence/s? | Apply WHS Risk Matrix | What action/s will be taken to eliminate the risk/s or at least reduce them to an acceptable level? | Apply WHS Risk Matrix | Who is responsible for putting controls in place? | When should the controls be put in place? | When were controls implemented? |
| Coach transport to and from Sydney | Vehicle accident, breakdown, or delayed return needing extended supervision needs. Likelihood: Unlikely; Consequence: Major. | High | Use NSW DoE-approved charter company with current maintenance and insurance Confirm driver accreditation and rest breaks. Seatbelts to be worn at all times Carry first-aid kit and emergency contact list. | Medium | Excursion Coordinator/ School Manager | Two weeks before excursion | Date of excursion |
| Movement through busy public areas (school to coach, Opera House forecourt, Circular Quay) | Students may become separated, lost, or injured in crowds. Likelihood: Possible; Consequence: Moderate. | High | Maintain 1:15 staff–student ratio. Allocate staff to front/rear of group and roll mark at key points. Provide all students with staff mobile numbers and meeting points. | Low | Supervising Teachers | On day of excursion | On day of excursion |
| Opera House venue hazards (stairs, seating, slips/trips) | Trip, slip, or fall causing injury. Likelihood: Possible; Consequence: Moderate. | Medium | Follow Sydney Opera House school safety briefing. Ensure students wear enclosed, non-slip footwear. • Staff to monitor stairwells and aisles during entry and exit. | Low | Supervising Teachers | Pre-departure briefing & day of excursion | On day of excursion |
| Medical or health emergencies | Asthma attack, allergic reaction, or other medical issue. Likelihood: Possible; Consequence: Major. | High | Collect updated medical/consent forms and emergency contacts. At least one staff member with current first-aid and anaphylaxis training. Carry students’ required medication (e.g., EpiPens, inhalers). | Medium | First-Aid Trained Staff & Excursion Coordinator | Prior to excursion | On day of excursion |
| Behavioural issues / non-compliance | Disruption, unsafe behaviour, or refusal to follow instructions leading to injury or missed transport. Likelihood: Possible; Consequence: Moderate. | Medium | Pre-excursion student briefing on behaviour expectations and consequences. Clear supervision plan and roll marking at each transition. Contact parents/guardians if serious behaviour occurs. | Low | Supervising Teachers | Pre-excursion briefing | On day of excursion |

## Risk matrix and evaluation

Table 1: THE WHS RISK MATRIX

|  |  | CONSEQUENCE (Severity) |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| LIKELIHOOD (Probability) |  | Insignificant 1 | Minor 2 | Moderate 3 | Major 4 | Critical 5 |
|  |  | No treatment required. | Injury/illness requiring first aid treatment only. | Injury/illness requiring hospitalisation on going treatment. | Life-threatening injury/illness or multiple hospitalisations. | Death or multiple life-threatening injuries. |
| Almost certain 5 | Expected to occur in most circumstances. | MEDIUM 5 | HIGH 10 | EXTREME 15 | EXTREME 20 | EXTREME 25 |
| Likely 4 | High probability of occurring in most circumstances. | MEDIUM 4 | MEDIUM 8 | HIGH 12 | EXTREME 16 | EXTREME 20 |
| Possible 3 | Might occur occasionally. | LOW 3 | MEDIUM 6 | HIGH 9 | HIGH 12 | EXTREME 15 |
| Unlikely 2 | Could occur at some time, doubtful. | LOW 2 | MEDIUM 4 | MEDIUM 6 | MEDIUM 8 | HIGH 10 |
| Rare 1 | May occur but only in exceptional circumstances. | LOW 1 | LOW 2 | LOW 3 | MEDIUM 4 | MEDIUM 5 |

Table 2: WHS Risk Evaluation

| Risk level | Acceptability | Priority for action to control risk | Sign-Off Authority: Schools | Sign-Off Authority: Other workplace |
| --- | --- | --- | --- | --- |
| Low 1-3 | Acceptable | PROCEED while monitoring existing controls. Manage the exposure to the hazard using existing procedures in consultation with workers and respond to any changes. | School Principal or delegate | Immediate Supervisor or Workplace Manager |
| Medium 4-8 | Tolerable | PROCEED with the activity and/or allow the hazard to persist only after identifying and implementing any additional controls reasonably practicable. Monitor all controls and manage the exposure to the hazard using existing procedures in consultation with workers and respond to any changes. | School Principal or delegate | Senior Manager or Director |
| High 9-14 | Unacceptable | DO NOT PROCEED and/or allow the hazard to persist until all risks/hazards are identified and the most effective control methods are documented in a risk assessment. Seek support from the workplace manager and WHS Advisor or the Incident Report and Support Hotline. | Principal to sign off. Principal to talk to staff about eliminating or reducing the risk, and contact: Health, Safety & Staff Wellbeing Directorate for review Legal as required. | Executive Director or delegate to talk to staff about eliminating or reducing the risk and contact: Health, Safety & Staff Wellbeing Directorate for review Legal as required. |
| Extreme 15+ | Unacceptable | STOP IMMEDIATELY and contact your WHS Advisor or the Incident Report and Support Hotline to plan a coordinated response in consultation with key subject matter experts to eliminate or control exposure to the hazard. | Principal to advise staff about eliminating or reducing the risk, and contact: Director Educational Leadership for review Health, Safety & Staff Wellbeing Directorate for review Legal as required. | Executive Director or delegate to advise staff about eliminating or reducing the risk, and contact: Health, Safety & Staff Wellbeing Directorate for review Legal as required. |

## Hierarchy of controls

| CONTROL | EFFECTIVENESS | DESCRIPTION | EXAMPLES |
| --- | --- | --- | --- |
| ELIMINATION | BEST | Eliminate the hazard entirely. | Eliminating the risk of a fall from height by doing the work at ground level. |
| SUBSTITUTION | VERY GOOD | Substitute the hazard with safer options. | Replacing hazardous cleaning chemicals with equivalent non-toxic products. |
| ISOLATION | GOOD | Isolate the hazard from causing harm. | Placing a barrier around an area of wet floor as a slipping hazard. |
| ENGINEERING | GOOD | Use engineering controls to reduce the risk. | Installing guards, rails, or handrails to prevent falls. |
| ADMINISTRATIVE | POOR | Administrate and document safe work practices. | Training workers in safe work procedures, Safe Operating Procedures. |
| PPE | WORST | Protect workers with Personal Protective Equipment (PPE). | Providing goggles and gloves to people handling hazardous chemicals. |